## Sheet1
Due | Day | Task | Sub-tasks | On Track? | Complete?
2015-10-26 | Monday | Proof of concept | Demonstrate ability of AR Drone to track red image. Use EZ-Builder built in tools. Record video of demo and write up task for report. | Yes | Yes
2015-10-31 | Saturday | Trade studies | Select development platform, writeup for report. Select development environment, writeup for report. Select open source support, writeup for report. | Yes | Yes
2015-11-02 | Monday | SW installs | Install the following tools in Linux box: - Netbeans - Qt Creator - DONE - ROS - Done - Git - DONE - Open CV - AR Drone SDK - DONE | No | No
2015-11-07 | Saturday | Development task | Complete Robohub tutorials | Due today | No
2015-11-07 | Saturday | Development task | Install ardrone_autonomy package | Yes | Yes
2015-11-07 | Saturday | Development task | Program drone to follow detection tag. | Due today | No
2015-11-10 | Tuesday | Partial report | Update report to include all work to date. Deliver partial report. | Yes | No
2015-11-17 | Tuesday | Development task | Program drone to follow color. | Yes | No
2015-11-24 | Tuesday | Development task | Program drone to follow image. | Yes | No
2015-12-15 | Tuesday | Final Report | Complete writeup for final report. Deliver final report. | Yes | No
2015-12-15 | Tuesday | Presentation | Complete presentation. Deliver presentation. | Yes | No
Tutorials
| Almost done w this one… | 1) http://robohub.org/up-and-flying-with-the-ar-drone-and-ros-getting-started/
2) http://robohub.org/up-and-flying-with-the-ar-drone-and-ros-joystick-control/
3) http://robohub.org/up-and-flying-with-the-ar-drone-and-ros-handling-feedback/
|  | AR Drone SDK install help | https://svn.ardrone.org/boards/1/topics/show/5942
http://gauth.fr/2011/09/introduction-to-the-ar-drone-sdk/
Formulas:
On Track? = IF([Complete?]="Yes","Yes",IF([Due]>TODAY(),"Yes",IF([Due]=TODAY(),"Due today","No")))