## Sheet1
ID | Task Description | Task Details | Due | Day | On Track? | Complete?
1 | Proof of concept | Demo drone color tracking ability - DONE Capture video of demo - DONE | 2015-10-26 | Monday | Yes | Yes
2 | Trade studies | Development platform - DONE Development environment - DONE Tools - DONE | 2015-10-31 | Saturday | Yes | Yes
3 | SW installs | ROS - Done Qt Creator - DONE Git - DONE AR Drone SDK - DONE Ardrone_Autonomy package - DONE | 2015-11-07 | Saturday | Yes | Yes
4 | Getting started | Complete Robohub tutorials Getting started - DONE Joystick control - SKIP Handling feedback - DONE | 2015-11-08 | Sunday | Yes | Yes
5 | Partial report | Update report to include all work to date Deliver partial report | 2015-11-17 | Tuesday | Yes | Yes
6 | SW installs | Open CV | 2015-11-17 | Tuesday | Yes | Yes | https://help.ubuntu.com/community/OpenCV
7 | Report: Related work | Complete section II.C "Related Work" | 2015-11-28 | Saturday | Due today | No
8 | Report: Tools | Complete section III.D "Development Tools" | 2015-11-29 | Sunday | Yes | No
9 | Development: tags | Detection tag tracking program | 2015-12-05 | Saturday | Yes | No | Did this as part of "Getting started" tutorial, should be able to play w this a bit more and then write up..
10 | Development: color | Color tracking program | 2015-12-05 | Saturday | Yes | No
11 | Development: image | Image tracking program | 2015-12-06 | Sunday | Yes | No
12 | Report: Follow-Me | Complete section III.E "Application Development" | 2015-12-12 | Saturday | Yes | No
13 | Report: Future Work | Complete section III.F "Future Work" | 2015-12-12 | Saturday | Yes | No
14 | Report: Results | Complete section IV "Results / Conclusions" | 2015-12-13 | Sunday | Yes | No
15 | Final Report | Complete writeup for final report Deliver final report | 2015-12-15 | Tuesday | Yes | No
16 | Presentation | Complete presentation Deliver presentation | 2015-12-15 | Tuesday | Yes | No
Tutorials
1) http://robohub.org/up-and-flying-with-the-ar-drone-and-ros-getting-started/
2) http://robohub.org/up-and-flying-with-the-ar-drone-and-ros-joystick-control/
3) http://robohub.org/up-and-flying-with-the-ar-drone-and-ros-handling-feedback/
AR Drone SDK install help
https://svn.ardrone.org/boards/1/topics/show/5942
http://gauth.fr/2011/09/introduction-to-the-ar-drone-sdk/
Open CV tutorials
http://petrkout.com/linux/parrot-ardrone-2-0-video-streaming-through-opencv-in-linux/
http://gauth.fr/2011/09/use-opencv-with-the-ar-drone-sdk/
http://gauth.fr/category/opencv/
Formulas:
On Track? = IF([Complete?]="Yes","Yes",IF([Due]>TODAY(),"Yes",IF([Due]=TODAY(),"Due today","No")))