## Sheet1
Due | Day | Task | Sub-tasks | On Track? | Complete?
2015-10-26 | Monday | Proof of concept | Demonstrate ability of AR Drone to track red image. Use EZ-Builder built in tools. Record video of demo and write up task for report. | Yes | Yes
2015-10-31 | Saturday | Trade studies | Select development platform, writeup for report. Select development environment, writeup for report. Select open source support, writeup for report. | Yes | Yes
2015-11-02 | Monday | SW installs | Install the following tools in Linux box: - Netbeans - ROS - Open CV - AR Drone SDK | Yes | No
2015-11-07 | Saturday | Development task | Program drone to follow detection tag. | Yes | No
2015-11-10 | Tuesday | Partial report | Update report to include all work to date. Deliver partial report. | Yes | No
2015-11-17 | Tuesday | Development task | Program drone to follow color. | Yes | No
2015-11-24 | Tuesday | Development task | Program drone to follow image. | Yes | No
2015-12-15 | Tuesday | Final Report | Complete writeup for final report. Deliver final report. | Yes | No
2015-12-15 | Tuesday | Presentation | Complete presentation. Deliver presentation. | Yes | No
Tool integration references:
|  | AR Drone and ROS: | http://robohub.org/up-and-flying-with-the-ar-drone-and-ros-getting-started/
|  | NetBeans and ROS: | http://wiki.ros.org/IDEs#NetBeans
|  | NetBeans and Open CV: | https://thefreecoder.wordpress.com/2012/09/10/use-netbeans-to-work-with-opencv-on-ubuntuand-linux-mint-and-other-distros-too/
Formulas:
On Track? = IF([Complete?]="Yes","Yes",IF([Due]>TODAY(),"Yes",IF([Due]=TODAY(),"Due today","No")))